## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3652556 | 68299 | ATM Project | 1 | ATM_1-1 | 292508 | Bug | 93046 | Login | 64212,63931 | ATM 1.1,ATM 1.0 | Wrong Pin Login Issue | If the card is inserted and a wrong pin is entered, It shows up a "Wrong PIN" message along with a line stating please enter the correct PIN and press enter. But, the system in here has a bug that makes the customer to enter the correct PIN twice before letting him in after a wrong attempt. Expected output: Should pop up just "Wrong pin" and let the customer enter the pin only once even after a wrong attempt to login to the account. Faulty output: Makes the customer to enter the pin multiple times after a wrong attempt. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319726 | LAB1-19 | Jan. 26, 2022 23:09 |  | 319726 | LAB1-19 | Jan. 31, 2022 20:24 | 0 | 0 | Jan. 31, 2022 20:24 LAB1-19 Bug still exists in version 1.1
3652696 | 68299 | ATM Project | 2 | ATM_1-2 | 292508 | Bug | 92843 | Display error | 64212,63931 | ATM 1.1,ATM 1.0 | Wrong accounts showing up in balance enquiry option. | When the card is inserted and logged in and the balance inquiry option is chosen, the system shows up wrong accounts for card 1. But gives accurate balances for the accounts linked to card 1. The expected output for card 1: Checking and Saving. Faulty output for card 1: Checking and Money Market. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319726 | LAB1-19 | Jan. 26, 2022 23:53 |  | 319726 | LAB1-19 | Feb. 02, 2022 15:39 | 0 | 0 | Jan. 31, 2022 20:25 LAB1-19 Bug still exists in version 1.1 | Feb. 02, 2022 15:39 LAB1-19 In this, the bug was partially resolved. But, later version software started to show all the accounts which are accessible along with the unaccessible accounts.
3652731 | 68299 | ATM Project | 3 | ATM_1-3 | 292508 | Bug | 92839 | Simulated Receipt Printer | 64212,63931 | ATM 1.1,ATM 1.0 | Wrong card details in the simulated receipt printer screen | Whenever any action is performed using cards 1 and 2 the ATM machine provides the action details of the card with improper numbers in the simulated receipt printer. If any action is performed using card 1, it gives the log information as card 2, and similarly, for card 2 it shows as card 3 in the log information in the simulated receipt printer area. The expected output for any action using card 1 and card 2: $100 withdrawn from card 1 and $200 withdrawn from card 2 Fault output for card 1: $100 withdrawn from card 2 Fault output for card 2: $200 withdrawn from card 3. Even though there is no evidence of any card 3 information presenting the ATM support document. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319726 | LAB1-19 | Jan. 27, 2022 00:01 |  | 319726 | LAB1-19 | Jan. 31, 2022 20:26 | 0 | 0 | Jan. 31, 2022 20:26 LAB1-19 Bug still exists in version 1.1
3653072 | 68299 | ATM Project | 4 | ATM_1-4 | 292508 | Bug | 92838 | Balance Enquiry | 63931 | ATM 1.0 | Balance fetching problem in card 2 | When we insert card 2 and proceed to check balances, the ATM display gives two account options for which the card has access (Checking and Money Market). It gives an accurate simulate receipt for the checking account but it does not perform any action and give any simulated receipt for the Money Market option, even if the card has access to this account. Expected Output: Accurately fetch balances for both the accounts in the given card. Fault Output: Shows no action of generating simulated receipt with balance details of the Money Market account for card 2. And it shows an invalid account type. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319726 | LAB1-19 | Jan. 27, 2022 00:11 |  | 319729 | Umesh Kumar Ravi | Jan. 31, 2022 20:17 | 0 | 0 | Jan. 31, 2022 20:17 Umesh Kumar Ravi This issue got resolved for "version 1.1".
3653114 | 68299 | ATM Project | 5 | ATM_1-5 | 292508 | Bug | 92843 | Display error | 63931 | ATM 1.0 | Spelling Mistake | In the whole process, when we are done with any type of transaction the ATM would ask us regarding any other activity we might want to do in the same session. But the display screen shows a constant error word "Wood" instead of "Would". Expected result: Would you like to do another transaction? Error result: Wood you like to do another transaction? | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319726 | LAB1-19 | Jan. 27, 2022 00:25 |  | 319727 | Aishwarya Satyasai Dantam | Jan. 31, 2022 19:24 | 0 | 0 | Jan. 31, 2022 19:24 Aishwarya Satyasai Dantam Resolved in version 1.1
3655292 | 68299 | ATM Project | 6 | ATM_1-6 | 292508 | Bug | 92957 | Transfer | 64212,63931 | ATM 1.1,ATM 1.0 | Display. | Display Options (for the "transfer" option) : After inserting the card (card 1) into the ATM, and entering the details for card 1, for access. we get display options as "Checking, Savings, and Money Market", where as the "card 1" has only 'checking and savings' accounts resulting in the display of 'money market' account being a bug. Similarly, after ejecting the card 1 and inserting the card 2 and entering the pin for access, we again get the display options as "Checking, Savings, and Money Market", where as the "card 2" has only 'checking and money market' accounts resulting in the display of 'savings account being a bug. For Card 1: [Display for Transfer] * Expected Output : "Checking" account and "Savings" account. * Actual Output (we got) : "Checking, Savings and Money Market" account. For Card 2: [Display for Transfer] * Expected Output : "Checking" account and "Money Market" account. * Actual Output (we got) : "Checking, Savings and Money Market" account. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319729 | Umesh Kumar Ravi | Jan. 27, 2022 20:51 |  | 319726 | LAB1-19 | Jan. 31, 2022 20:27 | 0 | 0 | Jan. 31, 2022 20:27 LAB1-19 Bug still exists in version 1.1
3655709 | 68299 | ATM Project | 7 | ATM_1-7 | 292508 | Bug | 92957 | Transfer | 63931 | ATM 1.0 | Transfer Operation for Card 1 | After inserting Card 1 and selecting the transfer operation to be performed, that is transferring of a certain amount from "checking to savings" account, an amount of "$0.5" is deducted from the actual amount and then the remaining amount is transferred to the destination account (savings). Similarly, if we transfer amount from "savings to checking" account, an amount of "$0.5" is deducted from the actual amount entered and then the remaining amount is transferred to the destination account (checking). Explanation: * Transfer from "Checking to Savings" : (a.) Expected Output : If an amount of "$40" is entered, then an amount of "$40" is transferred from "Checking" account to "Savings" account. (b.) Actual Output (we got) : If an amount of "$40" is entered, then an amount of "$39.5" is transferred from "Checking" account to "Savings" account. * Transfer from "Saving to Checking": (a.) Expected Output : If an amount of "$40" is entered, then the "$40" should be transferred from "Savings" account to "Checking" account. (b.) Actual Output (we got) : If an amount of "$40" is entered, then amount of "$39.5" is transferred from "Savings" account to "Checking" account. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319729 | Umesh Kumar Ravi | Jan. 27, 2022 21:51 |  | 319729 | Umesh Kumar Ravi | Jan. 31, 2022 20:12 | 0 | 0 | Jan. 31, 2022 20:12 Umesh Kumar Ravi Bugs got resolved for "version 1.1".
3655756 | 68299 | ATM Project | 8 | ATM_1-8 | 292508 | Bug | 92839,92957 | Simulated Receipt Printer,Transfer | 64212,63931 | ATM 1.1,ATM 1.0 | Wrong receipt details provided for a transfer | When the transfer process is happening, that is, If the transfer operation is performed from "checking to savings", It is being printed on the receipt that the operation being performed from "savings to checking" Similarly, it is happening for all other transfer operations between the available accounts. It always shows the opposite of the process which has been performed. * Expected Output: Process being performed from Money Market to Checking. Should print that the operation was performed from Money Market to Checking. * Faulty Output: Process being performed from Money Market to Checking. But the receipt shows the opposite i.e Checking to Money Market instead of Money Market to Checking. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319729 | Umesh Kumar Ravi | Jan. 27, 2022 22:14 |  | 319726 | LAB1-19 | Feb. 02, 2022 15:50 | 0 | 0 | Jan. 31, 2022 20:28 LAB1-19 Bug still exists in version 1.1
3655776 | 68299 | ATM Project | 9 | ATM_1-9 | 292508 | Bug | 92957 | Transfer | 63931 | ATM 1.0 | Transfer Operation for Card 2. | After inserting the Card 2 and selecting the transfer operation to be performed, that is transferring of certain amount from "checking to money market" account, an amount of "$0.5" is deducted from the actual amount and then the remaining amount is transferred to the destination account (money market). Similarly, if we transfer amount from "money market to checking" account, an amount of "$0.5" is deducted from the actual amount entered and then the remaining amount is transferred to the destination account (checking). Card 2: * Transfer from "Checking to Money Market" : (a.) Expected Output : If an amount of "$40" is entered, then an amount of "$40" is transferred from "Checking" account to "Money Market" account. (b.) Actual Output (we got) : If an amount of "$40" is entered, then an amount of "$39.5" is transferred from "Checking" account to "Money Market" account. * Transfer from "Money Market to Checking": (a.) Expected Output : If an amount of "$40" is entered, then the "$40" should be transferred from "Money Market" account to "Checking" account. (b.) Actual Output (we got) : If an amount of "$40" is entered, then amount of "$39.5" is transferred from "Money Market" account to "Checking" account. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319729 | Umesh Kumar Ravi | Jan. 27, 2022 22:24 |  | 319727 | Aishwarya Satyasai Dantam | Jan. 31, 2022 19:31 | 0 | 0 | Jan. 31, 2022 19:31 Aishwarya Satyasai Dantam Resolved in version 1.1
3657505 | 68299 | ATM Project | 10 | ATM_1-10 | 292508 | Bug | 93034 | Deposit | 64212,63931 | ATM 1.1,ATM 1.0 | Deposit Account Display | When we insert Card 1 into the ATM and select the deposit operation, the available accounts for depositing the money should be Checking and Savings accounts, instead Checking, Savings, and Money Market accounts are listed. Similarly, when inserting Card 2 and selecting the deposit operation to conduct, the available accounts to deposit the money should be Checking and Money Market accounts, but we again see Checking, Savings, and Money Market accounts resulting in a bug. Card 1: Expected Output: Display of Checking and Savings accounts Faulty Output: Displaying Checking, Savings, and Money Market accounts Card 2: Expected Output: Display of Checking and Money Market accounts Faulty Output: Displaying Checking, Savings, and Money Market accounts | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319728 | Ratna Sai Pravallika Kottam Setty | Jan. 28, 2022 16:33 |  | 319726 | LAB1-19 | Jan. 31, 2022 20:28 | 0 | 0 | Jan. 31, 2022 20:28 LAB1-19 Bug still exists in version 1.1
3657530 | 68299 | ATM Project | 11 | ATM_1-11 | 292508 | Bug | 93034 | Deposit | 64212,63931 | ATM 1.1,ATM 1.0 | Deposit Operation Defects for cards 1 and 2 | Following the insertion of Card and selection of the deposit operation to be performed, the deposit of a specific amount in a Checking account, an amount of $10 is deducted from the actual amount and the remaining amount is deposited to the Checking, Savings and Money Market accounts. Similarly, if we deposit money into a Savings account, $10 is deducted from the total amount entered, and the balance is deposited. Expected result: When we deposit $40 it should deposit $40 into the respective accounts. Faulty result: If we deposit $40 it deposits $30 into respective accounts. There is always a difference of $10. | 2 | In Progress | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319728 | Ratna Sai Pravallika Kottam Setty | Jan. 28, 2022 17:07 |  | 319728 | Ratna Sai Pravallika Kottam Setty | Feb. 02, 2022 15:54 | 0 | 0 | Jan. 31, 2022 20:03 Umesh Kumar Ravi Bug has been partially fixed, such as when the deposit operation takes place there is still an amount of "$0.10" gets deducted from the actual amount deposited.
3657531 | 68299 | ATM Project | 12 | ATM_1-12 | 292508 | Bug | 93211 | Log file | 64212,63931 | ATM 1.1,ATM 1.0 | Log data not clearing | When we log in with either card 1 or card 2 and perform some operations and log out, the log file still has the data of the operations performed and this log file is visible to the next user with a different card. Expected output: The log file should clear automatically when the person logs out with his card and the details should not be visible to the next user. Faulty Output: The log file is not cleared in time to time operations once the person logs out with his card and the log data is visible to others. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319728 | Ratna Sai Pravallika Kottam Setty | Jan. 28, 2022 17:09 |  | 319727 | Aishwarya Satyasai Dantam | Feb. 02, 2022 15:55 | 0 | 0 | Jan. 31, 2022 20:25 Umesh Kumar Ravi Bug still exists.
3657533 | 68299 | ATM Project | 13 | ATM_1-13 | 292508 | Bug | 93034 | Deposit | 64212,63931 | ATM 1.1,ATM 1.0 | Total and Available Balance Issue | Following the insertion of Card 1 and depositing funds into either a Checking or Savings account, the Total Balance and Available Balance should be the same, and the amount for each transaction should change. You can notice a change in the Total Balance with deduction of $10 from the amount deposited but no change in the Available Balance. Similarly, In Card 2, the Total Balance and Available Balance should be the same after depositing money in either a Checking or a Money Market account, and the amount for each transaction should change. The Total Balance has changed with deduction of $10 from the amount deposited, while the Available Balance has remained unchanged. Card 1: Expected Output: If an amount of $20 is deposited in Checking account, the Total and Available Balance should be $120. In Savings Account when you deposit $20 the Total and Available Balance should be $1020 Faulty Output: When we deposited $20 in Checking account, the Total and Available Balance is $110 and $100 respectively. In Savings Account when we deposit $20 the Total and Available Balance is $1010 and $1000 respectively. Card 2: Expected Output: If an amount of $20 is deposited in Checking account, the Total and Available Balance should be $120. In Money Market Account when you deposit $20 the Total and Available Balance should be $5020 Faulty Output: When we deposited $20 in Checking account, the Total and Available Balance is $110 and $100 respectively. In Money Market when we deposit $20 the Total and Available Balance is $5010 and $5000 respectively. | 2 | In Progress | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319728 | Ratna Sai Pravallika Kottam Setty | Jan. 28, 2022 17:11 |  | 319727 | Aishwarya Satyasai Dantam | Feb. 02, 2022 15:57 | 0 | 0 | Jan. 31, 2022 19:53 Aishwarya Satyasai Dantam Following the insertion of Card 1 and depositing funds into either a Checking or Savings account, the Total Balance and Available Balance should be the same, and the amount for each transaction should change. You can notice a change in the Total Balance with deduction of $0.10 from the amount deposited but no change in the Available Balance. Similarly, In Card 2, the Total Balance and Available Balance should be the same after depositing money in either a Checking or a Money Market account, and the amount for each transaction should change. The Total Balance has changed with deduction of $0.10 from the amount deposited, while the Available Balance has remained unchanged. Card 1: Expected Output: If an amount of $20 is deposited in Checking account, the Total and Available Balance should be $120. In Savings Account when you deposit $20 the Total and Available Balance should be $1020 Faulty Output: When we deposited $20 in Checking account, the Total and Available Balance is $119.90 and $100 respectively. In Savings Account when we deposit $20 the Total and Available Balance is $1019.90 and $1000 respectively. Card 2: Expected Output: If an amount of $20 is deposited in Checking account, the Total and Available Balance should be $120. In Money Market Account when you deposit $20 the Total and Available Balance should be $5020 Faulty Output: When we deposited $20 in Checking account, the Total and Available Balance is $119.90 and $100 respectively. In Money Market when we deposit $20 the Total and Available Balance is $5019.90 and $5000 respectively.
3657729 | 68299 | ATM Project | 14 | ATM_1-14 | 292508 | Bug | 93062 | Withdrawal | 64212,63931 | ATM 1.1,ATM 1.0 | Incorrect withdrawal account display for cards | On inserting Card 1 into the ATM and selecting withdraw option to perform withdrawal transaction,the display shows three accounts i.e checking,savings and money market but the available accounts with card1 are only checking and savings.Hence display of money market account is a bug in this case. Likewise is the case for card 2. On inserting Card 2 into the ATM and selecting withdraw option to perform withdrawal transaction,the display shows three accounts i.e checking,savings and money market but the available accounts with card 2 are only checking and money market.Hence display of savings account is a bug in this case. Card 1: Expected Output: Display of Checking and Savings accounts Faulty Output: Displaying Checking, Savings, and Money Market accounts Card 2: Expected Output: Display of Checking and Money Market accounts Faulty Output: Displaying Checking, Savings, and Money Market accounts | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319727 | Aishwarya Satyasai Dantam | Jan. 28, 2022 22:58 |  | 319726 | LAB1-19 | Jan. 31, 2022 20:30 | 0 | 0 | Jan. 31, 2022 20:30 LAB1-19 Bug still exists in version 1.1
3657753 | 68299 | ATM Project | 15 | ATM_1-15 | 292508 | Bug | 93062 | Withdrawal | 63931 | ATM 1.0 | Error in withdrawal function | On inserting the cards and selecting the withdrawal transaction type and choosing the account to withdraw from i.e. the checking account, ATM displays the following amount options $20 ,$40 ,$60 ,$100 & $200. Though checking account has an available balance of $100, entering any amount which is under this sufficient cash limit the display indicates insufficient funds available. Expected Output: If an amount of $20 is entered, then the amount of $20 should come out. Faulty Output: Message display-Insufficient cash available. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319727 | Aishwarya Satyasai Dantam | Jan. 28, 2022 23:34 |  | 319728 | Ratna Sai Pravallika Kottam Setty | Feb. 02, 2022 16:32 | 0 | 0 | Jan. 31, 2022 19:48 Umesh Kumar Ravi This issue gets solved after restarting the system (Please refer bug ATM_1-20 ).
3657758 | 68299 | ATM Project | 16 | ATM_1-16 | 292508 | Bug | 92838 | Balance Enquiry | 63931 | ATM 1.0 | Wrong action perfoming while balance enquiry. | When we try to insert card 1 and check the available balances in its linked accounts we have two major issues here. Accounts linked to card 1 are wrongly displayed. Displays Checking and Money Market instead of Checking and Savings. When we try to fetch balance in Money Market form card 1, it dispenses $500. Expected output: Should show "not authorized" when fetching balance from money market as the card is not linked to the money market. Faulty Output: Dispenses $500 when we check the balance for money market from card 1 and no amount is deducted from any of the linked and non-linked accounts. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319727 | Aishwarya Satyasai Dantam | Jan. 28, 2022 23:37 |  | 319727 | Aishwarya Satyasai Dantam | Feb. 02, 2022 16:05 | 0 | 0 | Jan. 31, 2022 19:56 Umesh Kumar Ravi This issue got resolved for "issue 1.1".
3657795 | 68299 | ATM Project | 17 | ATM_1-17 | 292508 | Bug | 93062 | Withdrawal | 63931 | ATM 1.0 | Withdrawal from Money Market in card 2 and Savings in card 1 | On inserting card 1 or card 2 ,selecting the withdrawal transaction type and choosing the account to withdraw from i.e the savings account in card 1 and money market in card 2, ATM displays the following amount options $20 ,$40 ,$60 ,$100 & $200. On entering $20, ATM gives $40. For $40 it gives $60. For $60 it gives $100 which are just random. Expected Output: If an amount of $20 is entered, then amount of $20 should come out. Faulty Output: Random amounts such as for $20 ,$40 are being given out by the ATM | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319727 | Aishwarya Satyasai Dantam | Jan. 29, 2022 00:08 |  | 319728 | Ratna Sai Pravallika Kottam Setty | Feb. 02, 2022 16:35 | 0 | 0 | Jan. 31, 2022 20:13 Aishwarya Satyasai Dantam Resolved in version 1.1
3658200 | 68299 | ATM Project | 18 | ATM_1-18 | 292508 | Bug | 93212 | Log off | 64212,63931 | ATM 1.1,ATM 1.0 | MFT: End session | MFT: On completing the transaction operations, the card ejects from the ATM machine but the system does not turn off on it's own Expected output: The system should turn off automatically. Faulty output: The system stays idle until the OFF button is pressed. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319728 | Ratna Sai Pravallika Kottam Setty | Jan. 29, 2022 17:08 |  | 319728 | Ratna Sai Pravallika Kottam Setty | Feb. 01, 2022 16:15 | 0 | 0 | Jan. 31, 2022 20:30 LAB1-19 Bug still exists in version 1.1 | Jan. 31, 2022 20:47 Aishwarya Satyasai Dantam Bug has not been rectified in version 1.1
3658202 | 68299 | ATM Project | 19 | ATM_1-19 | 292508 | Bug | 92843 | Display error | 64212 | ATM 1.1 | Display of dollar symbol | When we login with any card and perform any transaction,it does not reflect a dollor symbol for the amount of 60. Expected output:Should show $60 Faulty output: Shows 60. | 1 | Open | 2 | High | 64212 | ATM 1.1 |  |  | 319726 | LAB1-19 | 319728 | Ratna Sai Pravallika Kottam Setty | Jan. 29, 2022 17:10 |  | 319726 | LAB1-19 | Feb. 02, 2022 16:08 | 0 | 0
3658231 | 68299 | ATM Project | 20 | ATM_1-20 | 292508 | Bug | 93062 | Withdrawal | 63931 | ATM 1.0 | Withdrawal from Checking account for card 1 and card 2 | Restarting the whole system gives different output. Again on inserting card 1, selecting the withdrawal transaction type, and choosing the account to withdraw from i.e the checking account, ATM displays the following amount options $20 , $40, $60, $100 & $200.On entering $20,ATM dispenses $40.For $40,ATM dispenses $60 and so on.The same is the case with card 2. Expected Output: If an amount of $20 is entered, then the amount of $20 should come out. Faulty Output: Random amounts are being dispensed: For $20 it dispenses $40. For $40 it dispenses $60. For $60 it dispenses $100. For $100 it dispenses $200. For $200 it dispenses $20. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319727 | Aishwarya Satyasai Dantam | Jan. 29, 2022 21:05 |  | 319726 | LAB1-19 | Feb. 02, 2022 16:09 | 0 | 0 | Jan. 31, 2022 19:43 Umesh Kumar Ravi Bug got resolved for "version 1.1".
3658243 | 68299 | ATM Project | 21 | ATM_1-21 | 292508 | Bug | 92838,92843 | Balance Enquiry,Display error | 63931 | ATM 1.0 | MFT: Balance fetching problem for card 1 | MFT: When we insert card 1 and proceed to check balances, the ATM display gives two account options (Checking and Money Market). It gives an accurate simulate receipt for the checking account. For Money Market, the ATM displays an unknown error but it generates a receipt for the Money Market option. The amount indicated in the receipt is not of the money market account but is assumed to be of the savings account as the inquiry tab in the receipt reflects "SVGS". Expected Output: Accurately fetch balances for the accounts the card has access to. Fault Output: On selecting the money market account, ATM generates simulated receipt with balance details of the savings account. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319727 | Aishwarya Satyasai Dantam | Jan. 29, 2022 22:39 |  | 319726 | LAB1-19 | Feb. 02, 2022 16:14 | 0 | 0 | Jan. 31, 2022 19:24 Umesh Kumar Ravi Bug got resolved for "version 1.1". | Jan. 31, 2022 19:26 Umesh Kumar Ravi Bug got resolved for "version 1.1".
3660894 | 68299 | ATM Project | 23 | ATM_1-23 | 292508 | Bug | 93210 | Session | 63931 | ATM 1.0 | MFT: System hanging for invalid card - 3. | MFT: During the process of login, when we try to enter the wrong card instead of 1 or 2. The system works properly by recognizing the wrong card numbers above 3. But the system starts to hang if we try to log in using card 3. Expected output: Should display "Invalid Card" and eject the card if we insert any card apart from 1 or 2. Faulty Output: Works well for all cards above 3. But for card 3 the system hangs and does not let the user perform any task. | 3 | Resolved | 2 | High | 64212 | ATM 1.1 | 0 | Fixed | 319726 | LAB1-19 | 319726 | LAB1-19 | Jan. 31, 2022 17:15 |  | 319728 | Ratna Sai Pravallika Kottam Setty | Feb. 01, 2022 16:21 | 0 | 0 | Jan. 31, 2022 19:32 Umesh Kumar Ravi Bug got resolved for "version 1.1".